## Sheet1
Defect ID | Category Name | Title | Summary | Steps to Reproduce | Test Data | Expected Results | Actual Results | Related_To | Reported By | Assignee | Priority | Severity | Status | Attach | Comments of dev team | Comments of testing team
Swag_001 | Product page | All products have same photo | When user enter to products found all product have same photo | 1- open website 2- Enter valid data 3- Click login button | URL: https://www.saucedemo.com/ | Every product should have a unique photo | Same photo appear |  | ME |  | High | Low | Closed
Swag_002 | Product Page | Product photo doesn't match | When user click at any photo in product website it should go to same product in next page | 1- open website. 2-choose any product | URL: https://www.saucedemo.com/ | product photo should be same in product page and next page when user click on | The page that enter to it show different photo of product |  | ME |  | Medium | Low | Closed
Swag_003 | Product Page | Product Price doesn't match | Product price in product page is different of the price when user click at this product in next page | 1- open website. 2-choose any product | URL: https://www.saucedemo.com/ | product price should be same in the product page and next page when user click on | The page that enter to it show different price of product |  | ME |  | Medium | Low | Closed
Swag_004 | Product Page | User cant filter Name(A to Z) | When user filter product name from A to Z it oes not response | 1- Open website 2- Click on filter label 3- Choose name from A to Z | URL: https://www.saucedemo.com/ | Product name should show from A to Z | Filter choose doesn't happen |  | ME |  | Medium | Low | Closed
Swag_005 | Product Page | User cant filter Name(Z to A) | When user filter product name from Z to A it oes not response | 1- Open website 2- Click on filter label 3- Choose name from Z to A | URL: https://www.saucedemo.com/ | Product name should show from Z to A | Filter choose doesn't happen |  | ME |  | Medium | Low | Closed
Swag_006 | Product Page | User cant filter Price(Low to High) | When user filter product price from High to Low it does not response | 1- Open website 2- Click on filter label 3- Choose price from High to Low | URL: https://www.saucedemo.com/ | Product price should show from high to low | Filter choose doesn't happen |  | ME |  | Medium | Low | Closed
Swag_007 | Product Page | User cant filter Price(High to Low) | When user filter product price from Low to High it does not response | 1- Open website 2- Click on filter label 3- Choose price from Low to High | URL: https://www.saucedemo.com/ | Product price should show from low to high | Filter choose doesn't happen |  | ME |  | Medium | Low | Closed
Swag_008 | Product Page | User can not add more than two product on card in product page | when try to add more than first to product in product page user could not add any product | 1- Open website 2- click to add first and second product 3- click to add another any product | URL: https://www.saucedemo.com/ | user able to add any number of data in card | user can not add more than first and second product |  | ME |  | Medium | Low | Closed
Swag_009 | Product Page | User can not remove product from product page | when user try to remove product that added cant remove user should enter to card to remove it | 1- Open website 2- click to remove first or second product | URL: https://www.saucedemo.com/ | user able to remove product in product page | user can not delete product from product page |  | ME |  | Medium | Low | Closed
Swag_010 | Cart | User can not find total price in cart page | when user add peoduct and enter to card to continue buying product price dont add together | 1- Open website 2- click to add first and second product 3- click on card | URL: https://www.saucedemo.com/ | in card if user chooce more than product add price of them | product does not add if there more one |  | ME |  | Medium | Low | Reopen
Swag_011 | Cart | Product in next page does not add to card | when user click to any product in product page guide me to next page of product and try to add it to card it does not add | 1- Open website 2- click on any product in product page 3- add product to card | URL: https://www.saucedemo.com/ | user can add product to card in next page when user click to product | product does not add to card |  | ME |  | Medium | Low | Closed
Swag_012 | Cart | User cant complete data of checkout | when user go to card to continue buy it take only first name and when user complete to add second name and postal code dont accept and make change on first name | 1- Open website 2- click on any product in product page 3- click on checkout on card page 4- add first name and second and postal code | URL: https://www.saucedemo.com/ first name: yasmeen second name: dont accept data postal code:: dont accept data | user able to to complete data of buy | user does not able to add data of buy |  | ME |  | High | High | Closed
Swag_013 | Cart | User unable to complete the purchase | when user go to card to continue buy it take only first name and when user complete to add second name and postal code dont accept and make change on first name so user can not complete buying | 1- Open website 2- click on any product in product page 3- click on checkout on card page 4- add first name and second and postal code 5- continue | URL: https://www.saucedemo.com/ first name: yasmeen second name: dont accept data postal code:: dont accept data | user able to complete buy | user does not able to complete buy | #12 | ME |  | High | High | Closed